## Slide 1
Executive Update
Data & AI Portfolio
17 of 21 workstreams on track; a CISO review and a Fabric capacity call clear 3 of 4 risks
Data & AI – Oct 2026
Oct 22 – Nov 19, 2026
Status as of Thursday, October 22, 2026 · Prepared by Ron L'Esteve
OVERALL STATUS
At risk
17
On track
3
At risk
1
Blocked
21 workstreams in flight
Notes: Opening: 17 of 21 workstreams on track; a CISO review and a Fabric capacity call clear 3 of 4 risks

## Slide 2
EXECUTIVE SUMMARY
17 of 21 workstreams on track; a CISO review and a Fabric capacity call clear 3 of 4 risks
21
Workstreams in flight
17
On track
3
At risk
1
Blocked
6
Due in next 14 days
Health by platform
Chart: 
| Databricks | Microsoft Fabric | Power BI | Claude | ThoughtSpot
On track | 5 | 2 | 3 | 3 | 4
At risk | 0 | 1 | 1 | 1 | 0
Blocked | 0 | 0 | 0 | 1 | 0
What leadership should know
1
Cost and speed wins: serverless SQL cuts DBU spend 11% (~$6.2K/mo); Direct Lake reports load in 2.4s, down from 9.1s.
2
AI is reaching users: 32 of 45 ops managers on Spotter, and Copilot scores 88% on its 40-question test set.
3
Decide on Fabric F64 capacity by Oct 30, and have the CISO prioritize the stalled Claude Code pilot review.
Notes: Seventeen of twenty-one workstreams are green. The portfolio is amber because one item is blocked: the Claude Code pilot is waiting on an InfoSec reviewer. Three more are amber, two of them tied to Fabric capacity during month-end close.

## Slide 3
HIGHLIGHTS THIS WEEK
Faster reports, lower spend and safer releases are already landing
2.4s
Avg report load, down from 9.1s
POWER BI
Convert top 10 import models to Direct Lake
7 of 10 top models on Direct Lake, including Executive Scorecard; nightly refresh windows for those models are gone.
−11%
DBU spend, ~$6.2K/month saved
DATABRICKS
Serverless SQL migration + system-tables cost dashboard
3 of 4 SQL warehouses on serverless with auto-stop; cost dashboard live for Finance. On track for the 15% target.
9 / 12
Certified executive KPIs published
DATABRICKS
Unity Catalog metric views for certified executive KPIs
On-time delivery, cost per shipment and carrier scorecard reconcile to September close within ±0.2%.
9 min
Model deployment, down from ~2 hours
POWER BI
PBIP/TMDL + Git CI/CD for semantic models
21 of 25 semantic models deploy through Git CI/CD; automated checks have already blocked 3 non-compliant changes.
Notes: Direct Lake has cut average report load time from 9.1 to 2.4 seconds. Serverless SQL is already saving about 11% of DBU spend. Nine of twelve certified KPIs are live, and model deployments now take minutes instead of hours.

## Slide 4
RISKS & DECISIONS NEEDED
A CISO review and one Fabric capacity call clear three of the four risks
STATUS
WORKSTREAM & ISSUE
DECISION / ASK
NEEDED BY
BLOCKED
Claude Code pilot
Claude · DATA-29 · InfoSec review submitted Oct 13 has no reviewer; the pilot cannot start without approval.
Have the CISO prioritize the review this week, or the pilot slips to next sprint
Oct 23
AT RISK
Claude SSO + SCIM
Claude · DATA-26 · 120 users live; the ~600-user General group is delayed because nested Entra groups don't sync.
Confirm the flattened-group workaround so General users can be onboarded
Oct 23
AT RISK
Finance Q&A data agent
Microsoft Fabric · DATA-18 · Agent is 84% accurate, but F64 hit 97% at month-end close and responses slowed to 20s+.
Approve F128 (+$8.4K/mo) or off-peak refresh scheduling at no added cost
Oct 30
AT RISK
P-SKU to F-SKU migration
Power BI · DATA-38 · 31 of 38 workspaces moved; 7 Finance workspaces wait on capacity. P1 renews Nov 15.
Confirm the Oct 27–29 cutover window to avoid ~$4K/mo P1 renewal; $48K/yr savings
Nov 13
Notes: The asks are simple. We need the CISO to assign a reviewer for the Claude Code pilot, and a capacity decision on Fabric by October 30. The P-SKU exit keeps $48K a year in reach if we cut over Oct 27 to 29, ahead of the November 15 renewal.

## Slide 5
PORTFOLIO SCORECARD
Every platform is moving; the Claude rollout carries the most risk
Databricks
5 items ●5
Lakeflow pipeline migration
Due Nov 6
Serverless SQL + cost view
Due Nov 6
Certified KPI metric views
Due Nov 13
Governed Claude data access
Due Nov 13
Unity Catalog migration
Due Nov 6
Microsoft Fabric
3 items ●2 ●1
Finance Q&A data agent
Due Nov 20
OneLake zero-copy mirror
Due Nov 6
Fabric workspace governance
Due Nov 4
Power BI
4 items ●3 ●1
P-SKU to F-SKU migration
Due Nov 13
Semantic model CI/CD
Due Nov 6
Copilot readiness
Due Nov 4
Direct Lake conversion
Due Nov 13
Claude
5 items ●3 ●1 ●1
Claude Code pilot
Due Nov 20
Claude SSO + SCIM
Due Nov 13
Connector governance policy
Due Nov 4
Executive Deck skill
Due Nov 6
Claude policy + training
Due Nov 4
ThoughtSpot
4 items ●4
ThoughtSpot on gold layer
Due Nov 4
Liveboard version control
Due Nov 4
Spotter rollout to ops
Due Nov 13
ThoughtSpot SSO + access
Due Nov 6
Notes: Databricks, ThoughtSpot and Power BI are largely green. Claude has the only red item plus one amber on SSO provisioning for the General group. Fabric's amber is the capacity question.

## Slide 6
LOOKING AHEAD
Most in-flight work lands by mid-November; next four items are queued
Milestones due
Nov 4
6 due
Nov 6
7 due
Nov 13
6 due
Nov 20
2 due
Key milestones
Nov 6
Unity Catalog migration · Databricks
Nov 13
P-SKU to F-SKU migration · Power BI
Nov 13
Claude SSO + SCIM · Claude
Nov 20
Claude Code pilot · Claude
Nov 20
Finance Q&A data agent · Microsoft Fabric
Next up from the backlog
Embed Liveboards into customer portal
ThoughtSpot · Differentiated customer experience; premium analytics upsell
Agent Bricks shipment-exception triage agent
Databricks · Target 50% less manual exception triage; faster customer alerts
Claude Skills: MBR & RFP response
Claude · MBR prep time cut ~70%; faster, consistent RFP responses
AI/BI Genie spaces for Sales & Service
Databricks · Self-service answers on bookings, churn and case volumes
Notes: Most milestones land between November 4 and 13. Next from the backlog: customer-facing Liveboards, a shipment-exception triage agent, two new Claude skills, and Genie spaces for Sales and Service.